## Sheet1
Tasks: | Tarun Goel | Ruben Alvarez | Classes: | Board | Completed
Weeks |  |  |  | Player | Abandoned/New Approach
2018-10-15 | Blocks to be assigned to nodes | Game superclass responsible for all progress within the baord, moveForward() |  | Tree | In Progress
| Test Cases updated | New way for node to be defined by list instead |  | Spinner
2018-10-22 | Consider Players and pawn relationship | Enum research |  | Node
| Movements | More test cases |  | Game
2018-10-29 | Combining functionality | Scanner and user feedback |  | Main
| Exception handling | UI development |  | Block
2018-11-05 | Review Prepation | Money to be kept track of |  | Cards
Refactoring
2018-11-12 | TBD | TBD
2018-11-19
2018-11-26
2018-12-03
2018-12-10
2018-12-17
NOTE: Pair programming is employed most of the time