## Sheet1
Tasks: | Tarun Goel | Ruben Alvarez | Changes | Classes: | Board | Completed
Weeks |  |  |  |  | Player | Abandoned/New Approach
2018-10-15 | Blocks to be assigned to nodes | Exception handling |  |  | Tree | In Progress
| Test Cases updated | New way for node to be defined by list instead |  |  | Spinner
2018-10-22 | Consider Players and pawn relationship (Subclass Defined) | Enum research |  |  | Node
| Movements for players | More test cases in tandem with movement |  |  | Game
2018-10-29 | Combining functionality - moving/block logic/card/players | Scanner and user feedback | Defined well until now, will be moved to later stage |  | Main
| Cards Subclasses formulation - Action/House | Cards Subclasses formulation - Career/College Career Extends |  |  | Block
2018-11-05 | Review Prepation | Refactoring |  |  | Cards
| Game superclass to control gameplay | Blocks/Cards will return attibutes which need to be defined for Game
2018-11-12 | Game superclass responsible for all progress within the baord, moveForward() | UI development
| Money tracking | Objective for defining blocks and game
2018-11-19 | Combining functionality - moving/block logic/card/players | Scanner and user feedback
| Game changes | More test cases in tandem with movement
2018-11-26 | Inputs | Loops for movement
| Failsafe/Exception handling | Decks to use logic from tree/node
2018-12-03 | Merge functionality | Merge functionality
| Test Cases and UML update | Block Logic updated
2018-12-10 | Refactoring for more polymorphism | Block differences
| Final checks | Cleaning/refactoring
2018-12-17 | Clean code | Readible code
| Submission | Submission